## EN
Date | T2S Migration Schedule | CBF / T2S Business Day (CEST) | Revision | Revised Time (CEST) | Description of Event / Process of regular T2S Operational Day | CBF Comment
Friday, 8 September 2023 | until 18:45 |  |  |  | T2S Operational Day and CBF T2S Business Day will be executed based on the regular schedules
Friday, 8 September 2023 | 18:45 |  | è | Friday, 8 September 2023, 21:40 | T2S – Continue with Operating Day | On T2S, the new business day will start as soon as the preparations for the migration have been concluded.
Friday, 8 September 2023 |  | 19:00 | ü |  | CBF – Start of Day | CBF will change to value day, Monday, 11 September 2023, according to the regular schedule.
Friday, 8 September 2023 |  | 19:00 | ü |  | CBF Print Report: (settlement list)
Friday, 8 September 2023 |  |  | i | 19:30 | CBF: Completion end of day processing | The CBF business day 8 September 2023 to be closed and the End of Day (EoD) reporting will be prepared according to this timeline.
Friday, 8 September 2023 |  | 19:30 | è | Friday, 8 September 2023, 23:00 | KADI Reporting: MT564 – Notification MT568 – Narrative | CBF processing for corporate actions (KADI) will continue to be conducted according to the general procedures. This Friday, KADI reporting will be delivered later. This measure will ensure that all information coming from the KADI processing will be transmitted on the same day.
Friday, 8 September 2023 |  | 19:30 | è | Sunday, 10 September 2023, 09:00 | KADI Reporting: MT566 – Confirmations | The corporate action confirmations (MT566) will be available Sunday, 10 September 2023, at 09:00.
Friday, 8 September 2023 |  | 20:00 | ü |  | Clearstream Online Functionality | The CASCADE Online functionality (HOST / PC) and the Xact Web Portal will not be fully available during the migration phase. A separate time frame to access CASCADE Online Functonalities (HOST / PC) will be available on Sunday, 10 September 2023, between 07:30 and 11:30.
Friday, 8 September 2023 |  | 19:45 | è | Sunday, 10 September 2023, 07:00 | CBF's real-time interface to T2S | Clearstream will close its connectivity interface (T2S-I) to T2S while executing migration activities. Any instruction provided to CBF for T2S will be queued until Sunday, 10 September 2023, at around 07:00. This means that any instruction successfully transmitted will be on hold on connectivity layer.
Friday, 8 September 2023 |  |  | i | 20:00 | T2S: End of processing of incoming messages | Based on the T2S Migration Playbook, the CSDs will be informed by T2S that incoming messages through the existing connectivity channel will not be accepted anymore. clients acting in DCP mode are requested to monitor the message flow with T2S from this time on.
Friday, 8 September 2023 |  |  | i | 20:00 | T2S: Green Light for Migration | T2S will give "Green Light" for the Migration activities in close cooperation with the T2S Settlement Managers.
Friday, 8 September 2023 | 20:00 |  | è | Sunday, 10 September 2023, 04:10 | T2S – Start Night-time Settlement (NTS), Start First NTS Cycle | T2S will close the transfer queue for liquidity transfer on Friday, 8 September 2023 at around 18:50. The liquidity transfers initiated by clients in TARGET2 on will be related by T2S on Sunday, 10 September 2023, at around 03:30 so that the credit to the DCAs can be executed.
Friday, 8 September 2023 |  | 20:30 | ü |  | CASCADE Reporting: MT535 – Statement of Holdings
Friday, 8 September 2023 |  | 21:00 | û |  | CASCADE-RS – 4. Allocation run | During the T2S Migration Weekend this process will not be executed.
Friday, 8 September 2023 |  | 21:30 | ü |  | CASCADE-RS – Automated re-registration
Friday, 8 September 2023 | 22:20 |  | è | Sunday, 10 September 2023, 05:40 | T2S – End First NTS Cycle | According to the T2S Migration Playbook, the First NTS Cycle is expected to be completed on Sunday, 10 September 2023. The Last NTS Cycle will be started immediately afterwards.
Friday, 8 September 2023 | 22:20 |  | è | Sunday, 10 September 2023, 05:40 | T2S – Start Last NTS Cycle
Friday, 8 September 2023 |  | 22:30 | ü |  | Non-CCP SE trades are received from SE systems on trade date | Since the introduction of SET-GO, "Tagesgeschäfte" are forwarded for settlement according to the custody type, that is either to Creation or T2S. Trade confirmations provided by Stock Exchanges will be queued in the CBF system until until the migration activities are completed.
Friday, 8 September 2023 |  | 22:30 | è | Sunday, 10 September 2023, starting 07:30 | Newly arrived non-CCP SE trades in custody type CSC and NCSC-T are forwarded via SETI to T2S for settlement | The trade confirmations are queued. On Sunday, 10 September 2023, when CBF resumes settlement, the related settlement instructions will be created. Settlement feedback will be provided with the opening of the regular CBL operational day for the business day Monday, 11 September 2023.
Friday, 8 September 2023 |  | 22:30 | è | Sunday, 10 September 2023, starting 08:30 | Newly arrived non-CCP SE trades in custody type NCSC are forwarded via SETI to Creation for settlement | The trade confirmations are queued. On Sunday, 10 September 2023, once CBF resumes settlement, the related settlement instructions will be created. Since T2S will start on Sunday, 10 September 2023, at 06:30 the RTS processing, MT548 messages will be processed in real-time and MT537 is provided based on the clients' message subscription.
Friday, 8 September 2023 |  | 22:30 | û |  | CASCADE-RS – Transfer of RS instructions to share holder register for automated re-registration | The "CASCADE-RS 4. Allocation run" is not executed and hence such details will not be available.
Friday, 8 September 2023 |  |  | è | Friday, 8 September 2023, 23:00 | KADI Reporting: MT566 – Confirmation | Due to the change of the transmission time of the KADI reporting (MT564, MT568) from 19:30 to 23:00, the related confirmations (MT566) will be available on Sunday, 10 September 2023, 09:00.
Friday, 8 September 2023 |  | 23:00 | è | Sunday, 10 September 2023, starting at around 09:00 | CASCADE Reporting: MT536 – Statement of Transactions (Reporting Interval: Value in TAG 13A = 100) CBF Statement of Pending Transactions (MT537) (Reporting Interval: Value in TAG 13A = 651) MT586 – Statement of Allegements (Reporting Interval: Value in TAG 13A = 651) | The automated settlement reporting (CBF Outbound) will be queued until Sunday, 10 September 2023, 09:00. The indicated transmission time may change depending on the migration activities. This means that reporting is transmitted after the relevant milestone has been completed.
Friday, 8 September 2023 | 23:30 |  | è | Sunday, 10 September 2023, 06:30 | T2S – End Last NTS Cycle, End Night-time Settlement (NTS) | According to the T2S Migration Playbook, the NTS processing is completed on Sunday, 10 September 2023, 06:30.
Friday, 8 September 2023 | 23:30 |  | è | Sunday, 10 September 2023, 06:30 | T2S – Start Real-time Settlement (RTS) | According to the T2S Migration Playbook, the Real-time Processing will be executed on Sunday, 10 September 2023.
Sunday, 10 September 2023 |  |  | i | 3:00 | Point-of-No-Return (PoNR) | If not all CSDs in question can migrate, the other CSDs continue the migration process nevertheless.
Sunday, 10 September 2023 |  |  | i | 7:30 | Start of Transmission (A2A) T2S Settlement Messages / Reports | The T2S Migration SEP 2023 has been completed, and settlement reporting starts.
|  |  | ç | Sunday, 10 September 2023, 07:30 | Opening of CBF's automated connectivity channels and CASCADE Online Functionality | The automated connectivity channels as well as the CASCADE Online functionality (HOST / PC) will be open until the maintenance window will start on Sunday, 10 September 2023, at around 11:30.
Sunday, 10 September 2023 |  |  | i | 9:00 | Start of Transmission (A2A) Clearstream Settlement Reporting
|  | Saturday, 9 September 2023, 02:00 | è | Sunday, 10 September 2023, starting at 11:00 | CASCADE Reporting: MT536 – Statement of Transactions (Reporting Interval: Value in TAG 13A = 200) CBF Statement of Pending Transactions (MT537) (Reporting Interval: Value in TAG 13A = 801) MT586 – Statement of Allegements (Reporting Interval: Value in TAG 13A = 801) | The automated settlement reporting (CBF Outbound) will be queued until Sunday, 10 September 2023, 11:00. The indicated transmission time may change depending on the migration activities.
| 2:30 |  | è | Sunday, 10 September 2023, 11:30 | T2S – End Real-time Settlement (RTS)
| 2:30 |  | è | Sunday, 10 September 2023, 11:30 | T2S – Start Maintenance Window (MNTW) | After the Central Securities Depositories and the central banks agreed that the regular daily business schedule will become active, the maintenance windows will start.
|  | 3:00 | è | Sunday, 10 September 2023, 11:30 | CASCADE – End CASCADE Online | The CASCADE Online functionality (HOST / PC) will be available from Monday, 11 September 2023, at around 01:30.
|  | 3:00 | è | Sunday, 10 September 2023, 11:30 | Clearstream – Start Maintenance Window | The CBF maintenance window will be rescheduled. The maintenance activities will start once CBF completed all preceding T2S Migration SEP 2023 activities.
Monday, 11 September 2023 |  | 1:30 | ü |  | CASCADE – Start CASCADE Online The CBF T2S Business Day will be executed based on the regular schedule. | The CBF Online functionality (HOST / PC) will be opened for the upcoming business day.
Monday, 11 September 2023 | 2:30 |  |  |  | T2S – End Maintenance Window
Monday, 11 September 2023 | 2:30 |  |  |  | T2S – Start Real-time Settlement (RTS)
Monday, 11 September 2023 |  | 5:00 | ü |  | CASCADE Reporting: CBF Statement of Pending Transactions (MT537) (Reporting Interval: Value in TAG 13A = 041) MT586 – Statement of Allegements (Reporting Interval: Value in TAG 13A = 041) | These messages can contain results of T2S RTS Cycle scheduled on Saturday, 9 September 2023 at around 15:40.
Monday, 11 September 2023 |  | 5:00 | ü |  | KADI – Reporting and processing of market / reverse claims and transformation on settled underlying instructions resulting from the T2S NTS Cycle | This reporting will provide the results of the usual T2S Operational Day.
Legend:
Revision
ü | Processing in line with daily operational schedule
û | Process / reporting will not be executed
ç | Process ahead compared to daily operational schedule; see revised time
è | Process postponed compared to daily operational schedule; see revised time
i | information only for migration weekend; no corresponding process in the daily operational schedule