## EN
Date | T2S Release Schedule | CBF / T2S Business Day (CEST) | Revision | Revised Time (CEST) | Description of Event / Process of regular T2S Operational Day | CBF Comment
Monday, 13 November 2023 |  |  | i |  | CBF: T2S R2023.NOV Release Weekend Schedule | Publication of the "Indicative Timeline" in preparation of the deployment weekend.
Friday, 17 November 2023 | until 18:45 |  |  |  | T2S Operational Day and CBF T2S Business Day will be executed based on the regular schedules
Friday, 17 November 2023 | 18:45 |  | è | Saturday, 18 November 2023, 11:40 | T2S – Continue with Operating Day | On T2S, the new business day will start as soon as the deployment activities have been completed.
Friday, 17 November 2023 |  | 19:00 | ü |  | CBF – Start of Day | CBF will change to value day, Monday, 20 November 2023, according to the regular schedule.
Friday, 17 November 2023 |  | 19:00 | ü |  | CBF Print Report: (settlement list)
Friday, 17 November 2023 |  |  | i | 19:30 | CBF: Completion end of day processing | The CBF business day 17 November 2023 is closed and the End of Day (EoD) reporting will be prepared according to this timeline.
Friday, 17 November 2023 |  | 19:30 | è | Friday, 17 November 2023, 23:00 | KADI Reporting: MT564 – Notification MT568 – Narrative | CBF processing for corporate actions (KADI) will continue to be conducted according to the general procedures. This Friday, KADI reporting will be delivered later. This measure will ensure that all information coming from the KADI processing will be transmitted on the same day.
Friday, 17 November 2023 |  | 19:30 | è | Sunday, 19 November 2023, 08:00 | KADI Reporting: MT566 – Confirmations | The corporate action confirmations (MT566) will be available on Sunday, 19 November 2023, at 08:00.
Friday, 17 November 2023 |  | 20:00 | ü |  | Clearstream Online Functionality | The CASCADE Online functionality (HOST / PC) and Xact Web Portal will not be fully available during the implementation phase. A separate time frame to access CASCADE Online functonalities (HOST / PC) will be available on Sunday, 19 November 2023, between 06:30 and 11:00.
Friday, 17 November 2023 |  | 19:45 | è | Sunday, 19 November 2023, 06:00 | CBF's real-time interface to T2S | Clearstream will close its connectivity interface (T2S-I) to T2S while executing deployment activities. Any instruction provided to CBF for T2S will be queued until the implementation phase in CBF is finalised on Sunday, 19 November 2023, at around 06:00. This means that any instruction successfully transmitted will be on hold on connectivity layer.
Friday, 17 November 2023 |  |  | i | 20:00 | T2S: Green Light for software deployment | T2S will give "Green Light" for the deployment activities in close cooperation with the T2S Settlement Managers.
Friday, 17 November 2023 |  |  | i | 20:30 | T2S: End of processing of incoming messages | Based on the T2S Deployment Playbook, the CSDs will be informed by T2S that incoming messages through the existing connectivity channel will not be accepted anymore. Clients acting in DCP mode are requested to monitor the message flow with T2S from this time on.
Friday, 17 November 2023 | 20:00 |  | è | Saturday, 18 November 2023, 12:55 | T2S – Start Night-time Settlement (NTS), Start First NTS Cycle | T2S will close the transfer queue for liquidity transfers on Friday, 17 November 2023 at around 18:45. The liquidity transfers initiated by clients in TARGET2 will be related by T2S on Saturday, 18 November 2023, at around 13:25 so that credits to the DCAs can be executed.
Friday, 17 November 2023 |  | 20:30 | ü |  | CASCADE Reporting: MT535 – Statement of Holdings
Friday, 17 November 2023 |  | 21:00 | û |  | CASCADE-RS – 4. Allocation run | During the T2S Release Weekend this process will not be executed.
Friday, 17 November 2023 |  | 21:30 | ü |  | CASCADE-RS – Automated re-registration
Friday, 17 November 2023 |  | 21:30 | è | Sunday, 19 November 2023, starting 08:00 | CBF Statement of Pending Transactions (MT537) (Reporting Interval: Value in TAG 13A = 651) MT586 – Statement of Allegements (Reporting Interval: Value in TAG 13A = 651) | Due to the implementation activities, the reports will be delivered on Sunday, 19 November 2023, 08:00.
Friday, 17 November 2023 | 22:20 |  | è | Saturday, 18 November 2023, 14:25 | T2S – End First NTS Cycle | According to the T2S Deployment Playbook, the First NTS Cycle is expected to be completed on Saturday, 18 November 2023. The Last NTS Cycle will be started immediately afterwards.
Friday, 17 November 2023 | 22:20 |  | è | Saturday, 18 November 2023, 14:25 | T2S – Start Last NTS Cycle
Friday, 17 November 2023 |  | 22:30 | ü |  | Non-CCP SE trades are received from SE systems on trade date | Since the introduction of SET-GO, "Tagesgeschäfte" are forwarded for settlement according to the custody type, that is either to Creation or T2S. Trade confirmations provided by stock exchanges will be queued in the CBF system until the deployment activities are completed.
Friday, 17 November 2023 |  | 22:30 | è | Sunday, 19 November 2023, starting 07:30 | Newly arrived non-CCP SE trades in custody type CSC and NCSC-T are forwarded via SETI to T2S for settlement | The trade confirmations are queued. On Sunday, 19 November 2023, once the deployment actvities in CBF are finalised, the related settlement instructions will be created. Since T2S will start the RTS processing on Saturday, 18 November 2023, at 16:55, MT548 messages will be processed in real-time and MT537 is provided based on the clients' message subscriptions.
Friday, 17 November 2023 |  | 22:30 | è | Sunday, 19 November 2023, starting 07:30 | Newly arrived non-CCP SE trades in custody type NCSC are forwarded via SETI to Creation for settlement | The trade confirmations are queued. On Sunday, 19 November 2023, once the deployment actvities in CBF are finalised, the related settlement instructions will be created. CBL will finalise its implementation activities in the course of Saturday, 18 November 2023. Settlement feedback will be provided with the opening of the regular CBL operational day for the business day Monday, 20 November 2023.
Friday, 17 November 2023 |  | 22:30 | û |  | CASCADE-RS – Transfer of RS instructions to share holder register for automated re-registration | The "CASCADE-RS 4. Allocation run" is not executed and hence such details will not be available.
Friday, 17 November 2023 |  | 23:00 | è | Sunday, 19 November 2023, starting at around 08:00 | KADI Reporting: MT566 – Confirmation | Due to the implementation activities, the related confirmations (MT566) will be available on Sunday, 19 November 2023, 08:00.
Friday, 17 November 2023 |  | 23:00 | è | Sunday, 19 November 2023, starting at around 08:00 | CASCADE Reporting: MT536 – Statement of Transactions (Reporting Interval: Value in TAG 13A = 100) | Due to the implementation activities, the reports will be delivered on Sunday, 19 November 2023, 08:00.
Friday, 17 November 2023 | 23:30 |  | è | Saturday, 18 November 2023, 15:15 | T2S – End Last NTS Cycle, End Night-time Settlement (NTS) | According to the T2S Deployment Playbook, the NTS processing is completed on Saturday, 18 November 2023, 15:15.
Friday, 17 November 2023 | 23:30 |  | è | Saturday, 18 November 2023, 16:55 | T2S – Start Real-time Settlement (RTS) | According to the T2S Deployment Playbook, the Real-time Processing will be executed on Saturday, 18 November 2023.
Saturday, 18 November 2023 |  |  | i | 17:00 | Start of Transmission (A2A) T2S Settlement Messages / Reports
|  |  | ç | Sunday, 19 November 2023, 06:30 | Opening of CBF's automated connectivity channels and CASCADE Online functionality | The automated connectivity channels as well as the CASCADE Online functionality (HOST / PC) will be open until the maintenance window will start on Sunday, 19 November 2023, at around 11:00.
Sunday, 19 November 2023 |  |  | i | 8:00 | Start of Transmission (A2A) Clearstream Settlement Reporting | The CBF deployment activities for T2S Release R2023.NOV are completed, and settlement reporting starts.
|  | Saturday, 18 November 2023, 02:00 | è | Sunday, 19 November 2023, starting at 10:00 | CASCADE Reporting: MT536 – Statement of Transactions (Reporting Interval: Value in TAG 13A = 200) CBF Statement of Pending Transactions (MT537) (Reporting Interval: Value in TAG 13A = 801) MT586 – Statement of Allegements (Reporting Interval: Value in TAG 13A = 801) | The automated settlement reporting (CBF Outbound) will be queued until Sunday, 19 November 2023, 10:00. The indicated transmission time may change depending on the implementation activities. This means that reporting is transmitted after the relevant milestone has been completed.
| 2:30 |  | è | Sunday, 19 November 2023, 10:50 | T2S – End Real-time Settlement (RTS)
| 2:30 |  | è | Sunday, 19 November 2023, 11:00 | T2S – Start Maintenance Window (MNTW) | After the Central Securities Depositories and the central banks agreed that the regular daily business schedule will become active, the maintenance windows will start.
|  | Saturday, 18 November 2023, 03:00 | è | Sunday, 19 November 2023, 11:00 | CASCADE – End CASCADE Online | The CASCADE Online functionality (HOST / PC) will be available from Monday, 20 November 2023, at around 01:30.
|  | Saturday, 18 November 2023, 03:00 | è | Sunday, 19 November 2023, 11:00 | Clearstream – Start Maintenance Window | The CBF maintenance window will be rescheduled. The maintenance activities will start once CBF completed all preceding T2S R2023.NOV activities.
Monday, 20 November 2023 |  | 1:30 | ü |  | CASCADE – Start CASCADE Online The CBF T2S Business Day will be executed based on the regular schedule. | The CBF Online functionality (HOST / PC) will be opened for the upcoming business day.
Monday, 20 November 2023 | 2:30 |  | ç | Sunday, 19 November 2023 21:00 | T2S – End Maintenance Window
Monday, 20 November 2023 | 2:30 |  | ç | Sunday, 19 November 2023 21:00 | T2S – Start Real-time Settlement (RTS)
Monday, 20 November 2023 |  | 5:00 | ü |  | CASCADE Reporting: CBF Statement of Pending Transactions (MT537) (Reporting Interval: Value in TAG 13A = 041) MT586 – Statement of Allegements (Reporting Interval: Value in TAG 13A = 041) | These messages can contain results of T2S RTS Cycle scheduled on Saturday, 18 November 2023 at around 15:40.
Monday, 20 November 2023 |  | 5:00 | ü |  | KADI – Reporting and processing of market / reverse claims and transformations on settled underlying instructions resulting from the T2S NTS Cycle | This reporting will provide the results of the usual T2S Operational Day.
Legend:
Revision
ü | Processing in line with daily operational schedule
û | Process / reporting will not be executed
ç | Process ahead compared to daily operational schedule; see revised time
è | Process postponed compared to daily operational schedule; see revised time
i | information only for release weekend; no corresponding process in the daily operational schedule