## EN
Date | T2S Release Schedule | CBF / T2S Business Day (CEST) | Revision | Revised Time (CEST) | Description of Event / Process of regular T2S Operational Day | CBF Comment
Monday, 3 June 2024 |  |  | i |  | CBF: T2S R2024.JUN Release Weekend Schedule | Publication of the "Indicative Timeline" in preparation of the deployment weekend.
Friday, 7 June 2024 | until 18:45 |  |  |  | T2S Operational Day and CBF T2S Business Day will be executed based on the regular schedules
Friday, 7 June 2024 | 18:45 |  | è | Saturday, 8 June 2024, 11:40 | T2S – Continue with Operating Day | On T2S, the new business day will start as soon as the deployment activities have been completed.
Friday, 7 June 2024 |  | 19:00 | ü |  | CBF – Start of Day | CBF will change to value day, Monday, 10 June 2024, according to the regular schedule.
Friday, 7 June 2024 |  | 19:00 | ü |  | CBF Print Report: (settlement list)
Friday, 7 June 2024 |  |  | i | 19:30 | CBF: Completion end of day processing | The CBF business day 7 June 2024 is closed and the End of Day (EoD) reporting will be prepared according to this timeline.
Friday, 7 June 2024 |  | 19:30 | è | Friday, 7 June 2024, 23:00 | KADI Reporting: MT564 – Notification MT568 – Narrative | CBF processing for corporate actions (KADI) will continue to be conducted according to the general procedures. This Friday, KADI reporting will be delivered later. This measure will ensure that all information coming from the KADI processing will be transmitted on the same day.
Friday, 7 June 2024 |  | 19:30 | è | Sunday, 9 June 2024, 08:00 | KADI Reporting: MT566 – Confirmations | The corporate action confirmations (MT566) will be available on Sunday, 9 June 2024, at 08:00.
Friday, 7 June 2024 |  | 20:00 | ü |  | Clearstream Online Functionality | The CASCADE Online functionality and Xact Web Portal will not be fully available during the implementation phase. A separate time frame to access CASCADE Online functonalities will be available on Sunday, 9 June 2024, between 06:30 and 11:00.
Friday, 7 June 2024 |  | 19:45 | è | Sunday, 9 June 2024, 06:00 | CBF's real-time interface to T2S | Clearstream will close its connectivity interface (T2S-I) to T2S while executing deployment activities. Any instruction provided to CBF for T2S will be queued until the implementation phase in CBF is finalised on Sunday, 9 June 2024, at around 06:00. This means that any instruction successfully transmitted will be on hold on connectivity layer.
Friday, 7 June 2024 |  |  | i | 20:00 | T2S: Green Light for software deployment | T2S will give "Green Light" for the deployment activities in close cooperation with the T2S Settlement Managers.
Friday, 7 June 2024 |  |  | i | 20:30 | T2S: End of processing of incoming messages | Based on the T2S Deployment Playbook, the CSDs will be informed by T2S that incoming messages through the existing connectivity channel will not be accepted anymore. Clients acting in DCP mode are requested to monitor the message flow with T2S from this time on.
Friday, 7 June 2024 | 20:00 |  | è | Saturday, 8 June 2024, 18:55 | T2S – Start Night-time Settlement (NTS), Start First NTS Cycle | T2S will close the transfer queue for liquidity transfers on Friday, 7 June 2024 at around 18:45. The liquidity transfers initiated by clients in TARGET2 will be related by T2S on Saturday, 8 June 2024, at around 17:50 so that credits to the DCAs can be executed.
Friday, 7 June 2024 |  | 20:30 | ü |  | CASCADE Reporting: MT535 – Statement of Holdings
Friday, 7 June 2024 |  | 21:00 | û |  | CASCADE-RS – 4. Allocation run | During the T2S Release Weekend this process will not be executed.
Friday, 7 June 2024 |  | 21:30 | ü |  | CASCADE-RS – Automated re-registration
Friday, 7 June 2024 |  | 21:30 | è | Sunday, 9 June 2024, starting 08:00 | CBF Statement of Pending Transactions (MT537) (Reporting Interval: Value in TAG 13A = 651) MT586 – Statement of Allegements (Reporting Interval: Value in TAG 13A = 651) | Due to the implementation activities, the reports will be delivered on Sunday, 9 June 2024, 08:00.
Friday, 7 June 2024 | 22:20 |  | è | Saturday, 8 June 2024, 20:25 | T2S – End First NTS Cycle | According to the T2S Deployment Playbook, the First NTS Cycle is expected to be completed on Saturday, 8 June 2024. The Last NTS Cycle will be started immediately afterwards.
Friday, 7 June 2024 | 22:20 |  | è | Saturday, 8 June 2024, 20:25 | T2S – Start Last NTS Cycle
Friday, 7 June 2024 |  | 22:30 | ü |  | Non-CCP SE trades are received from SE systems on trade date | Since the introduction of SET-GO, "Tagesgeschäfte" are forwarded for settlement according to the custody type, that is either to Creation or T2S. Trade confirmations provided by stock exchanges will be queued in the CBF system until the deployment activities are completed.
Friday, 7 June 2024 |  | 22:30 | è | Sunday, 9 June 2024, starting 07:30 | Newly arrived non-CCP SE trades in custody type CSC and NCSC-T are forwarded via SETI to T2S for settlement | The trade confirmations are queued. On Sunday, 9 June 2024, once the deployment actvities in CBF are finalised, the related settlement instructions will be created. Since T2S has already started the RTS processing on Saturday, 8 June 2024, at 22:55, MT548 messages will be processed in real-time and MT537 is provided based on the clients' message subscriptions.
Friday, 7 June 2024 |  | 22:30 | è | Sunday, 9 June 2024, starting 07:30 | Newly arrived non-CCP SE trades in custody type NCSC are forwarded via SETI to Creation for settlement | The trade confirmations are queued. On Sunday, 9 June 2024, once the deployment actvities in CBF are finalised, the related settlement instructions will be created. CBL will finalise its implementation activities in the course of Saturday, 8 June 2024. Settlement feedback will be provided with the opening of the regular CBL operational day for the business day Monday, 10 June 2024.
Friday, 7 June 2024 |  | 22:30 | û |  | CASCADE-RS – Transfer of RS instructions to share holder register for automated re-registration | The "CASCADE-RS 4. Allocation run" is not executed and hence such details will not be available.
Friday, 7 June 2024 |  | 23:00 | è | Sunday, 9 June 2024, starting at around 08:00 | KADI Reporting: MT566 – Confirmation | Due to the implementation activities, the related confirmations (MT566) will be available on Sunday, 9 June 2024, 08:00.
Friday, 7 June 2024 |  | 23:00 | è | Sunday, 9 June 2024, starting at around 08:00 | CASCADE Reporting: MT536 – Statement of Transactions (Reporting Interval: Value in TAG 13A = 100) | Due to the implementation activities, the reports will be delivered on Sunday, 9 June 2024, 08:00.
Friday, 7 June 2024 | 23:30 |  | è | Saturday, 8 June 2024, 21:15 | T2S – End Last NTS Cycle, End Night-time Settlement (NTS) | According to the T2S Deployment Playbook, the NTS processing is completed on Saturday, 8 June 2024, 21:15.
Friday, 7 June 2024 | 23:30 |  | è | Saturday, 8 June 2024, 22:55 | T2S – Start Real-time Settlement (RTS) | According to the T2S Deployment Playbook, the Real-time Processing will be executed on Saturday, 8 June 2024, 22:55.
Saturday, 8 June 2024 |  |  | i | 23:00 | Start of Transmission (A2A) T2S Settlement Messages / Reports
|  |  | ç | Sunday, 9 June 2024, 06:00 | Opening of CBF's automated connectivity channels and CASCADE Online functionality | The automated connectivity channels as well as the CASCADE Online functionality will be open until the maintenance window will start on Sunday, 9 June 2024, at around 11:00.
Sunday, 9 June 2024 |  |  | i | 8:00 | Start of Transmission (A2A) Clearstream Settlement Reporting | The CBF deployment activities for T2S Release R2024.JUN are completed, and settlement reporting starts.
|  | Saturday, 8 June 2024, 02:00 | è | Sunday, 9 June 2024, starting at 10:00 | CASCADE Reporting: MT536 – Statement of Transactions (Reporting Interval: Value in TAG 13A = 200) CBF Statement of Pending Transactions (MT537) (Reporting Interval: Value in TAG 13A = 801) MT586 – Statement of Allegements (Reporting Interval: Value in TAG 13A = 801) | The automated settlement reporting (CBF Outbound) will be queued until Sunday, 9 June 2024, 10:00. The indicated transmission time may change depending on the implementation activities. This means that reporting is transmitted after the relevant milestone has been completed.
| 2:30 |  | è | Sunday, 9 June 2024, 10:50 | T2S – End Real-time Settlement (RTS)
| 2:30 |  | è | Sunday, 9 June 2024, 11:00 | T2S – Start Maintenance Window (MNTW) | After the Central Securities Depositories and the central banks agreed that the daily business schedule will continue to be followed, the maintenance window will start.
|  | Saturday, 8 June 2024, 03:00 | è | Sunday, 9 June 2024, 11:00 | CASCADE – End CASCADE Online | The CASCADE Online functionality will be available from Monday, 10 June 2024, at around 01:30.
|  | Saturday, 8 June 2024, 03:00 | è | Sunday, 9 June 2024, 11:00 | Clearstream – Start Maintenance Window | The CBF maintenance window will be rescheduled. The maintenance activities will start once CBF completed all preceding T2S R2024.JUN activities.
Monday, 10 June 2024 |  | 1:30 | ü |  | CASCADE – Start CASCADE Online The CBF T2S Business Day will be executed based on the regular schedule. | The CBF Online functionality will be opened for the upcoming business day.
Monday, 10 June 2024 | 2:30 |  | ç | Sunday, 9 June 2024 21:00 | T2S – End Maintenance Window
Monday, 10 June 2024 | 2:30 |  | ç | Sunday, 9 June 2024 21:00 | T2S – Start Real-time Settlement (RTS)
Monday, 10 June 2024 |  | 5:00 | ü |  | CASCADE Reporting: CBF Statement of Pending Transactions (MT537) (Reporting Interval: Value in TAG 13A = 041) MT586 – Statement of Allegements (Reporting Interval: Value in TAG 13A = 041) | These messages can contain results of T2S RTS Cycle scheduled on Saturday, 8 June 2024 at around 15:40.
Monday, 10 June 2024 |  | 5:00 | ü |  | KADI – Reporting and processing of market / reverse claims and transformations on settled underlying instructions resulting from the T2S NTS Cycle | This reporting will provide the results of the usual T2S Operational Day.
Legend:
Revision
ü | Processing in line with daily operational schedule
û | Process / reporting will not be executed
ç | Process ahead compared to daily operational schedule; see revised time
è | Process postponed compared to daily operational schedule; see revised time
i | information only for release weekend; no corresponding process in the daily operational schedule