## R2026.NOV - PBI Fixes
Reference | T2S PBI Title (Summary) | ICP / DCP | T2S PBI Short Description (BOD) | Status
PBI 239160 | T2S NRO test observation - Fix of U2A code - It is possible to click the sign button twice during the NRO signing process, which causes the PIN pop-up to occur more than once. | DCP | 1. Business Scenario Description: During an NRO Instruction you need to sign the instruction before you can execute it 2. Issue Description: It is possible to click the sign button twice during the NRO signing process, which causes the PIN pop-up to occur more than once. 3. Possible Workaround: Don´t double-click the sign button 4. TARGET Services concerned: T2S 5. Effects and restrictions on concerned TARGET Service: You have to enter your PIN twice, or in some cases the signing process needs to be redone. 6. Required Change: For the T2S GUI the NRO signing process needs to be adapted, so that the Sign button can no longer be clicked more than once, ensuring that the PIN needs only to be entered once, to submit the instruction. | Scheduled for R2026.NOV; go live 16 November 2026
PBI 239546 | Error code PMMO02 when reallocating penalties in 4-Eyes mode | DCP | 1. Business Scenario Description: In the context of T2S Penalty Management, penalty reallocation (RALO) allows a participant to transfer a penalty from one failing party to another via the T2S GUI. When performing a reallocation with four-eyes, the initiating user submits the request and a second user authorizes it. During this process, the user must select the New Failing Party BIC. When both BICs are identical e.g. Intra CSD Participant Scenario, the T2S Reference of the failed Settlement Instruction must be provided. 2. Issue Description: For the specific case of penalty reallocations initiated via GUI under the four-eyes rule, the request is not executed showing the following error: PMMO025 -"The T2S reference of the failed Settlement Instruction is neither the delivering nor the receiving Settlement Instruction created in T2S from the already matched." This occurs because the T2S Reference of the Settlement Instruction is not correctly stored in the database. During the four-eyes business validation, the system retrieves the reference incorrectly, and therefore the reference no longer matches any valid settlement instruction in T2S, triggering error PMMO025. 3. Workaround: The penalty re-allocation of an Intra CSD Participant instruction can be done A2A and U2A without four-eyes. 4. TARGET Services concerned: T2S 5. Effects and restrictions on concerned TARGET Service: This issue impacts penalty reallocation operations (RALO) performed via GUI under four-eyes. As a result, valid reallocation requests are systematically not executed and rejected at business validation (the second step of the four-eyes process), preventing users from completing penalty reallocation processes that require four-eyes control. 6. Required SW change: Amend the system to ensure that the T2S Reference of the failing Settlement Instruction field is correctly stored in the database. | Scheduled for R2026.NOV; go live 16 November 2027
PBI 239629 | semt.002 / semt.018 is not reporting Account Owner correctly when there is no Activity | DCP | 1. Business Scenario Description: When retrieving a semt.002 and semt.018 report, the account owner is reported in the field <AcctOwnr><Id/></AcctOwnr> 2. Issue Description: When the activity Indicator in the semt.002 and semt.018 report is false, the field <Ac-ctOwnr><Id/></AcctOwnr> is empty 3. Workaround: n/a 4. TARGET Services concerned: T2S 5. Effects and restrictions on concerned TARGET Service: For semt.002 and semt.018 reports without activity, the account owner is not reported 6. Required SW Change: The software must be adapted to include the account owner also in cases where the activity indicator is false. | Scheduled for R2026.NOV; go live 16 November 2028
PBI 240029 | Impossibility to update primary CMB to include BIC as authorized BIC | cash DCP | 1. Business Scenario Description: CRDM User trying to insert an Authorised BIC inside a T2S CMB. 2. Issue Description: Business Rule DCU6048, checking for duplicate Authorised BIC Rules, is erroneously triggered. This issue happens under a very specific circumstance. Let's say that a given CMB has three Authorised BICs: A, B and C. At a given point in time, BIC C is permanently deleted by the responsible Party. Afterwards, the very same BIC C is inserted in 4-eyes mode but with the second step being revoked by the approving user. Due to a software bug this will cause a data inconsistency, leading to the described Business Rule to be triggered even if the BIC C is correctly not shown in the GUI. 3. Workaround: No workaround available, LLI feasible. 4. TARGET Services concerned: T2S. 5. Effects and restrictions on concerned TARGET Service: In the described particular scenario, the BIC under analysis cannot be authorized anymore. 6. Required SW change: To improve reference data management, in revoke case, for the described scenario. 7. CRDM object: CMB. | Scheduled for R2026.NOV; go live 16 November 2029